## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
e-shopping
Group 21 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-09 |  |  |  |  | September | [6 empty] | October | [27 empty] | November
Scrolling Increment: | 323 | time axis 2022-09-28 to 2022-11-22
Milestone description | Category | Assigned to | Progress | Start | Days | [56 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | time axis 2022-09-28 to 2022-11-22
Iteration 01
Iteration planning and meeting | Goal | All members | 25% | 2021-09-14 | 1 | 2022-10-01: 2
Complete stakeholder register | High Risk | All members | 100% | 2021-09-15 | 5 | bar: 2022-10-02 to 2022-10-06
Design persona | Low Risk | All members | 50% | 2021-09-20 | 8 | bar: 2022-10-07 to 2022-10-14
Review and test persona | Med Risk | Wang keyi&Li yufan | 75% | 2021-09-24 | 4 | bar: 2022-10-12 to 2022-10-15
Complete progress report | On Track | Wang keyi&Li yufan | 100% | 2021-09-28 | 3 | bar: 2022-10-16 to 2022-10-18
Reflection | On Track | All members | 10% | 2021-10-01 | 1 | bar: 2022-10-18
Iteration 02
Make Gantt chart | On Track |  | 20% | 2021-10-12 | Unknown | bar: 2022-10-29 to 2022-11-01
Group Meeting2 | On Track |  | 100% | 2021-10-16 | 4 | bar: 2022-11-02 to 2022-11-05
Complete Resource Requirement List | On Track |  | 100% | 2021-10-20 | 4 | bar: 2022-11-06 to 2022-11-09
Complete progress report2 | On Track |  | 100% | 2021-10-24 | 4 | bar: 2022-11-10 to 2022-11-13
Add new data to Gantt chart | On Track |  | 60% | 2021-10-28 | Unknown
Iteration 03
Complete risk Register | On Track |  | 100% | 2021-11-07 | 2
Complete user Acceptance Test Results | On Track |  | 100% | 2021-11-09 | 1
Group Meeting3 | On Track |  | 100% | 2021-11-10 | 2
Complete progress report3 | On Track |  | 100% | 2021-11-10 | 2
complete Gantt chart for second time | On Track |  | 100% | 2021-11-12 | 1
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-09 |  |  |  |  | November | [20 empty] | December
Scrolling Increment: | 1 | time axis 2021-11-10 to 2022-01-04
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-09 | 3 | W: 2; T: 2
Task 2 | Milestone |  |  | 2021-11-14 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2021-11-06 | 10
Task 4 | Milestone |  |  | 2021-11-29 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2021-11-15 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-15 | 13
Task 2 | On Track |  | 50% | 2021-11-17 | 9
Task 3 | Low Risk |  | 33% | 2021-11-22 | 11
Task 4 | Milestone |  |  | 2021-11-24 | 1 | bar: W
Task 5 |  |  |  | 2021-11-25 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-24 | 4
Task 2 | Med Risk |  |  | 2021-11-27 | 14
Task 3 | On Track |  |  | 2021-12-12 | 6
Task 4 | Goal |  |  | 2021-12-16 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2021-11-15 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-19 | 15
Task 2 |  |  |  | 2022-01-02 | 5
Task 3 | Milestone |  |  | 2022-02-13 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-09 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 5 | time axis 2021-11-14 to 2022-01-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-14 to 2022-01-08
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-09 | 3
Task 2 | Milestone |  |  | 2021-11-14 | 1 | bar: 2021-11-14
Task 3 | Low Risk |  | 50% | 2021-11-06 | 10
Task 4 | Milestone |  |  | 2021-11-29 | 1 | bar: 2021-11-29
Task 5 | Med Risk |  | 10% | 2021-11-15 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-15 | 13
Task 2 | On Track |  | 50% | 2021-11-17 | 9
Task 3 | Low Risk |  | 33% | 2021-11-22 | 11
Task 4 | Milestone |  |  | 2021-11-24 | 1 | bar: 2021-11-24
Task 5 |  |  |  | 2021-11-25 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-24 | 4
Task 2 | Med Risk |  |  | 2021-11-27 | 14
Task 3 | On Track |  |  | 2021-12-12 | 6
Task 4 | Goal |  |  | 2021-12-16 | 3 | 2021-12-16: 2; 2021-12-17: 2; 2021-12-18: 2
Task 5 | Low Risk |  |  | 2021-11-15 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-19 | 15
Task 2 |  |  |  | 2022-01-02 | 5
Task 3 | Milestone |  |  | 2022-02-13 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one